## Gantt Chart - Data Collection
Gantt Chart - Data Collection (Page 1)
Task ID | Task Name | Start Date | End Date | Status | % Complete
T001 | Define Data Requirements | 2023-10-01 | 2023-10-05 | In Progress | 75%
T002 | Design Data Collection Forms | 2023-10-06 | 2023-10-15 | In Progress | 55%
T003 | Develop Survey Tool | 2023-10-16 | 2023-10-25 | Not Started | 0%
T004 | Pilot Testing (Phase 1) | 2023-10-26 | 2023-11-05 | Not Started | 0%
T005 | Analyze Pilot Results | 2023-11-06 | 2023-11-15 | Not Started | 0%
Gantt Timeline View (Page 1)
Task IDTimeline Progress BarT001●●T002●●T003T004T005
Gantt Chart - Data Collection (Page 2)
Task ID | Task Name | Start Date | End Date | Status | % Complete
T006 | Finalize Data Collection Instruments | 2023-11-16 | 2023-11-30 | Not Started | 0%
T007 | Train Field Staff | 2023-12-01 | 2023-12-05 | Not Started | 0%
T008 | Execute Data Collection (Phase 1) | 2023-12-06 | 2024-01-15 | Not Started | 0%
T009 | Data Validation and Cleaning | 2024-01-162024-01-31Not Started
T010 | Data Analysis & Reporting | 2024-02-01 | 2024-03-15 | In Progress
35%
Gantt Timeline View (Page 2)
Task IDTimeline Progress BarT006T007T008T009T010●●
Note: This multi-page Gantt chart template is designed for data collection projects. Each page represents a phase of the project timeline.