## Office Use Gantt Chart Template
Project Gantt Chart - Data Collection
Task ID | Task Description | Start Date | End Date | Status
1 | Define Data Requirements | 2024-04-01 | 2024-04-05 | In Progress
1.1 | Identify Data Sources | 2024-04-06 | 2024-04-15 | Not Started
1.2 | Design Data Collection Forms | 2024-04-16 | 2024-04-19 | Completed
1.3 | Conduct Field Data Collection | 2024-04-20 | 2024-05-15 | In Progress
1.4 | Data Validation & Cleaning | 2024-05-16 | 2024-06-15 | Not Started
M1 | Data Collection Milestone 1 - Completion | 2024-05-15 | 2024-05-15 | Not Started