## Worksheet
Task ID | Task Name | Start Date | Due Date | Status | Progress (%)
T001 | Data Requirement Gathering | 2024-07-01 | 2024-07-15 | In Progress | 65%
T002 | Define Data Sources | 2024-07-16 | 2024-07-31 | Not Started | 0%
T003 | Survey Design and Approval | 2024-08-01 | 2024-08-15 | Not Started | 0%
T004 | Data Collection - Field Phase | 2024-08-16 | 2024-09-30 | Not Started | 5%
T005 | Data Validation and Cleaning | 2024-10-01 | 2024-10-15 | Not Started | 0%
T006 | Final Data Review & Sign-off | 2024-10-16 | 2024-10-31 | Not Started | 0%
M001 | Project Kickoff | 2024-07-01 | 2024-07-01 | Completed | 100%
M002 | Data Collection Complete | 2024-10-31 | 2024-10-31 | Not Started | 0%