## Worksheet
Data Collection Gantt Chart
Project Timeline & Task Progress - Professional Template
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status
T001 | Define Research Objectives | 2023-10-02 | 2023-10-05 | 4
Design Data Collection Instruments | T002 | 2023-10-06 | 2023-10-15 | 9
T003 | Recruit Participants | 2023-10-16 | 2023-10-25 | 9
T004 | Conduct Data Collection Phase 1 | 2023-10-26 | 2023-11-15 | 20
T005 | Conduct Data Collection Phase 2 | 2023-11-16 | 2023-11-30 | 15
T006 | Validate Data Quality | 2023-12-01 | 2023-12-15 | 14
T007 | Data Cleaning & Preparation | 2023-12-16 | 2024-01-15 | 30
T008 | Finalize Data Collection Report | 2024-01-16 | 2024-01-31 | 15
© 2023 Professional Data Collection Gantt Chart Template ¦ For Internal Use Only