## Worksheet
Small Business Gantt Chart - Data Collection
Task ID | Task Name | Start Date | End Date | Status | % Complete
1.01 | Define Data Collection Objectives | 2024-04-01 | 2024-04-03 | In Progress | 75%
1.02 | Identify Target Data Sources | 2024-04-04 | 2024-04-05 | In Progress | 90%
1.03 | Design Data Collection Forms/Tools | 2024-04-06 | 2024-04-10 | To Do | 0%
1.04 | Test Collection Tools with Pilot Group | 2024-04-11 | 2024-04-13 | To Do | 0%
1.05 | Deploy Full Data Collection Phase | 2024-04-14 | 2024-04-28 | To Do | 0%
M1 | Data Collection Phase Complete | 2024-04-30 | 2024-04-30 | Milestone Achieved | 100%
Note:This Gantt chart template is designed for small business data collection projects. Update status and dates as needed.