## Worksheet
Team Use Gantt Chart - Data Collection
Task ID | Task Name | Owner | Start Date | End Date | Status | Progress (%)
T001 | Define Data Collection Goals | Project Lead | 2023-10-01 | 2023-10-05 | Done
T002 | Identify Data Sources | Research Analyst | 2023-10-06 | 2023-10-15 | In Progress
T003 | Design Data Collection Forms | UX Designer | 2023-10-16 | 2023-10-25 | Pending
T004 | Develop Data Collection Tools | Dev Team Lead | 2023-10-26 | 2023-11-15 | Pending
T005 | Test Data Collection Process | QA Specialist | 2023-11-16 | 2023-11-30 | Pending
T006 | Deploy and Train Team | Training Coordinator | 2023-12-01 | 2023-12-15 | Pending
T007 | Begin Data Collection Phase | Data Manager | 2023-12-16 | 2024-01-31 | Pending
T008 | Data Validation & Cleaning | Analytics Lead | 2024-02-01 | 2024-03-31 | Pending
Template Version 1.0 ¦ Created for Team Use ¦ Last Updated: October 2023