## Monthly Planner - Client View
Monthly Planner - Client View
Data Collection Template ¦ Month:, Year:
Date | Daily Activities |  |  | Progress Status |  | Notes/Comments
| Task Name | Priority | Assigned To | Completion (%) | Status (✓/✗)
Jan 1 | Project Kickoff Meeting | High | John Doe |  | ✓ | Initial planning discussed.
Jan 2 | Client Requirements Gathering | High | Jane Smith |  | ✗ | Waiting for client feedback.
Jan 3 | Design Mockups Review | Medium | Alex Brown |  | ✓ | Approved by client.
Jan 4 | Bug Fixing Sprint | High | Team A |  | ✗ | 3 bugs remaining.
Jan 5 | Documentation Update | Low | Lisa Wong |  | ✗ | Partial completion.