## Worksheet
DATA COLLECTION PLANNER TEMPLATE (EXTENDED VERSION)
Week | Date Range | Data Collection Objective | Methodology | Responsible Person | Status | Notes / Remarks | Action Items / Follow-ups
Week 1 | 01/04/2024 - 07/04/2024 | Initial baseline data gathering for project A | Survey & Interviews (Online Form) | John Doe | Pending | Target: 50 participants
Week 2 | 08/04/2024 - 14/04/2024 | Field observation and validation of collected data | On-site Observation & Field Audit | Jane Smith | In Progress | Verify response accuracy from week 1.
Week 3 | 15/04/2024 - 21/04/2024 | Secondary data integration from external sources | Data Scraping & API Integration | Alex Brown | Completed | Verified source: Government Open Data Portal v3.1.
Week 4 | 22/04/2024 - 28/04/2024 | Data cleaning and quality assurance check | Automated Script & Manual Review | Sarah Lee | Pending | Remove duplicates and outliers.
Week 5 | 29/04/2024 - 05/05/2024 | Data analysis and preliminary reporting | Statistical Analysis using R & Visualization (Tableau) | Michael Chen | To Do | Generate summary charts and insights.
Week 6 | 06/05/2024 - 12/05/2024 | Stakeholder review and feedback integration | Workshop & Feedback Session | Lisa White | To Do | Present findings to core team.
Project Overview & Progress Summary
Overall Status: |  | In Progress (60% Complete) |  |  | Pending approval and final validation
Instructions: Update each cell as task progresses. Use 'Completed', 'In Progress', or 'Pending' for Status column.