## Worksheet
Data Collection Planner Template - Planning View
Task ID | Task Description | Responsible Team | Start Date | End Date | Status
T001 | Define Data Collection Objectives | Project Management | 2024-01-15 | 2024-01-25 | In Progress
T002 | Develop Data Collection Tools | Data Team | 2024-01-18 | 2024-01-31 | In Progress
T003 | Validate Questionnaire with Pilot Group | Quality Assurance | 2024-01-28 | 2024-02-15 | Pending Review
T004 | Deploy Data Collection Phase 1 (Online) | Field Operations | 2024-02-16 | 2024-03-15 | To Do
T005 | Gather Field Data (In-Person Surveys) | Field Agents | 2024-03-18 | 2024-04-15 | To Do
T006 | Data Cleaning and Validation | Data Analysts | 2024-04-16 | 2024-05-15 | To Do
T007 | Final Report Compilation and Review | Reporting Team | 2024-05-16 | 2024-06-30 | To Do