## Worksheet
Project Plan - Advanced Template
Purpose:Data Collection ¦Template Type:Project Plan ¦Last Updated:April 5, 2024
ID | Task Description | Owner | Start Date | Due Date | Status | Priority | Budget (USD)
P001 | Define project scope and objectives | Jane Smith | 2024-04-01 | 2024-04-05 | In Progress | High | $5,000
P002 | Develop data collection framework | Mark Johnson | 2024-04-06 | 2024-04-15 | Pending | High | $8,500
P003 | Design survey instruments and templates | Sarah Lee | 2024-04-16 | 2024-04-25 | Pending | Medium | $6,300
P004 | Recruit and train field data collectors | David Brown | 2024-04-18 | 2024-05-10 | Pending | High | $12,000
P005 | Deploy field data collection operations | Emily Davis | 2024-05-11 | 2024-06-15 | Pending | Medium | $9,800
P006 | Data validation and quality checks | Robert Clark | 2024-06-16 | 2024-07-15 | Pending | Medium | $7,400
P007 | Data analysis and reporting preparation | Lisa Morgan | 2024-07-16 | 2024-08-15 | Pending | High | $15,200
P008 | Finalize project report and deliverables | Thomas Reed | 2024-08-16 | 2024-09-15 | Pending | High | $3,500
Total Estimated Budget: | [6 empty] | $68,700