## Worksheet
Annual Project Plan - Data Collection
Project Phase | Task Description | Responsible Team/Person | Scheduled Start Date | Scheduled End Date | Status (Planned/In Progress/Completed) | Budget Allocation (USD)
Planning & Requirements Gathering | Define data collection objectives and scope for the year | Project Manager, Data Lead | 01-Jan-2024 | 15-Feb-2024 | Planned | $8,500
Data Source Identification | Identify internal and external data sources for collection | Data Analyst, IT Team | 16-Feb-2024 | 15-Mar-2024 | Planned | $6,000
Data Collection Tools Setup | Configure data collection tools and APIs as needed | IT Team, DevOps Engineer | 16-Mar-2024 | 30-Apr-2024 | Planned | $15,000
Data Collection Campaign (Q2) | Execute data collection for Q2 initiatives and user feedback cycles | Field Team, Data Collectors | 01-May-2024 | 31-Jul-2024 | Planned | $55,000
Data Quality Assurance & Validation | Review and validate collected data for accuracy and consistency | Data Quality Team, QA Analysts | 01-Aug-2024 | 31-Aug-2024 | Planned | $8,500
Data Integration & Storage Setup | Integrate data into central repository with proper security protocols | Database Admin, Security Officer | 01-Sep-2024 | 30-Sep-2024 | Planned | $18,750
Analytics & Reporting Preparation (Q3) | Prepare dashboards and reports for Q3 insights | Data Analyst, BI Team | 01-Oct-2024 | 31-Dec-2024 | Planned | $52,500
Total Annual Budget: | [5 empty] | $164,250
This project plan template is designed for annual data collection activities. Update status regularly and conduct monthly reviews.