## Project Plan - Data Collection
Project Plan - Data Collection
Purpose:Data Collection
Template Type:Project Plan
Style/Version:Business Use
ID | Task Name | Description | Responsible Person | Start Date | End Date | Status
1.01 | Data Requirements Gathering | Define data needs and sources for the project. | John Doe | 2024-04-05 | 2024-04-12 | In Progress
1.02 | Design Data Collection Instruments | Create forms, surveys, and tools for data capture. | Jane Smith | 2024-04-13 | 2024-04-19 | Not Started
1.03 | Test Data Collection Tools | Pilot test forms and ensure usability. | Mary Johnson | 2024-04-20 | 2024-04-26 | Not Started
1.04 | Begin Data Collection Phase 1 | Collect data from primary sources. | Robert Brown | 2024-04-27 | 2024-05-10 | To Do
1.05 | Data Validation & Cleaning | Verify data accuracy and remove duplicates. | Sarah Davis | 2024-05-11 | 2024-05-17 | To Do
1.06 | Data Analysis Preparation | Organize data for analytical processing. | James Wilson | 2024-05-18 | 2024-05-24 | To Do
1.07 | Data Analysis & Reporting | Analyze collected data and generate reports. | Linda Garcia | 2024-05-25 | 2024-06-07 | To Do
1.08 | Review & Finalize Findings | Presentation and validation of results with stakeholders. | Michael Lee | 2024-06-08 | 2024-06-14 | To Do
Generated on: 2024-04-05 ¦ Version: 1.0 ¦ Prepared by: Project Management Office