## Project Plan - Compact Template
Task ID | Task Name | Responsible Person | Start Date | End Date | Status
T001 | Project Initiation | Jane Doe | 2023-10-01 | 2023-10-05 | In Progress
T002 | Data Requirements Gathering | John Smith
T003 | Data Source Identification | Alice Brown | 2023-10-16 | 2023-10-25 | Not Started
T004 | Data Collection Execution | Mike Wilson | 2023-10-26 | 2023-11-15 | Not Started
T005 | Data Validation & Cleaning | Sarah Lee | 2023-11-16 | 2023-11-30 | Not Started
T006 | Data Analysis & Reporting | David Kim | 2023-12-01 | 2023-12-15 | Not Started
T007 | Final Review & Submission | Jane Doe | 2023-12-16 | 2023-12-20 | Not Started