## Project Plan - Data Version
Task ID | Task Description | Responsible Person | Status | Start Date | End Date | Duration (Days)
Phase 1: Project Initiation
P1-001 | Define project objectives and scope | Project Manager | To Do | 2024-04-01 | 2024-04-05 | 5
P1-002 | Identify stakeholders and key contacts | Project Coordinator | In Progress | 2024-04-03 | 2024-04-15 | 13
Phase 2: Data Collection Planning
P2-001 | Develop data collection instruments (forms, surveys) | Data Analyst | In Progress | 2024-04-10 | 2024-04-25 | 16
P2-002 | Validate data collection tools with pilot group | Data Scientist | To Do | 2024-04-26 | 2024-05-10 | 15
Phase 3: Data Collection Execution
P3-001 | Deploy data collection across target population | Data Collector Team | To Do | 2024-05-11 | 2024-06-30 | 51
P3-002 | Monitor and ensure data quality during collection | Data Quality Officer | To Do | 2024-05-11 | 2024-06-30
Phase 4: Project Closure & Reporting
P4-001 | Compile final dataset and perform quality checks | Data Analyst | To Do | 2024-07-01
P4-002 | Prepare and present final project report | Project Manager | To Do | 2024-07-15
General Metrics & Notes
Total Tasks: |  |  | 10
Completed Tasks: |  |  | 0
On Track: |  |  | 2
Delayed Tasks: |  |  | 0