## Worksheet
# | Task Name | Start Date | End Date | Duration (Days) | Assignee | Milestones |  |  |  | Progress (%) | Notes
[6 empty] | Phase 1 | Phase 2 | Phase 3 | Final Delivery
12023-10-012023-10-055✓100%
22023-10-062023-10-151080%Stakeholder interviews completed.
3Design Phase2023-10-162023-10-3015Alex Brown60%UI/UX prototypes approved by client.
4Development2023-10-312023-12-15< t d style = "text-align: center;" > 45< t d > Team A (8 members) | 30%
< t d style = "text-align: center;" > 6< t d > Client Review & Feedback2024-01-062024-01-1510< t d > Project Manager< | 5%
< t d style = "text-align: center;" > 7Final Delivery & Handover2024-01-162024-01-3115< t d > Project Manager & Team A |  |  | <✓0%
Total Duration:55 days