## Worksheet
Project Plan - Financial View
Project Phase | Budget (USD) | Actual Spend (USD) | Remaining Budget (USD) | Status | Notes
Initiation | $25,000 | $8,500 | $16,500 | On Track | Initial planning and stakeholder alignment completed.
Planning | $50,000 | $42,300 | $7,700 | On Track | Budget slightly over by $2,300 due to scope expansion.
Execution | $120,000 | $65,450 | $54,550 | On Track | Construction and development in progress.
Monitoring & Control | $30,000 | $27,800 | $2,200 | On Track | Regular audits and reporting underway.
Closure | $15,000 | $3,200 | $11,800 | On Track | Final documentation and client sign-off pending.
Total | $240,000 | $147,250 | $92,750