## Worksheet
Project Plan - Freelancer Template
Task ID | Task Description | Start Date | End Date | Status | Assigned To | Budget (USD)
001 | Project Kickoff Meeting | 2024-04-05 | 2024-04-05 | Pending | Jane Smith | $150.00
002 | Requirement Analysis | 2024-04-06 | 2024-04-15 | In Progress | Mark Johnson | $500.00
003 | Wireframing and Design | 2024-04-16 | 2024-04-30 | Pending | Sarah Lee | $850.00
004 | Front-End Development | 2024-05-01 | 2024-05-15 | Pending | Dave Chen | $1,600.00
005 | Back-End Development | 2024-05-16 | 2024-06-15 | Pending | Lisa Park | $3,200.00
006 | Testing & QA | 2024-06-16 | 2024-07-15 | Pending | Ryan White | $950.00
007 | User Training & Documentation | 2024-07-16 | 2024-07-31 | Pending | Amy Green | $650.00
008 | Project Final Review & Handover | 2024-08-01 | 2024-08-15 | Pending | Jane Smith (Lead) | $550.00
Total Estimated Budget: | [5 empty] | $8,450.00