## Worksheet
Project Plan Template
Purpose: Data Collection ¦ Template Type: Project Plan ¦ Style/Version: Large Business
Phase | Task Name | Start Date | End Date | Responsible Team/Person | Status | Milestones
Project Initiation
Phase 1 | Define Project Scope | 2024-04-01 | 2024-04-15 | Project Manager & Stakeholders | In Progress | Scope Document Approved
Phase 1 | Stakeholder Identification & Engagement | 2024-04-03 | 2024-04-18 | Project Coordinator | Pending | Stakeholder List Finalized
Planning & Design
Phase 2 | Develop Detailed Project Plan | 2024-04-16 | 2024-05-15 | Project Management Office (PMO) | Draft Ready for Review
Phase 2 | Resource Allocation & Budget Planning | 2024-04-18 | 2024-05-10 | Finance & HR Team
Phase 2 | Design System Architecture (if applicable) | 2024-05-01 | 2024-05-31 | IT & Engineering Teams
Execution & Development
Phase 3 | Resource Mobilization & Team Onboarding | 2024-05-16 | 2024-05-31 | HR & Operations
Phase 3 | Core Development & Implementation (MVP) | 2024-06-01 | 2024-08-31 | Development Team (Agile Sprints)
Phase 3 | Quality Assurance & Testing Cycles | 2024-07-15 | 2024-09-15 | QA Team & UAT Lead
Monitoring & Control
Phase 4 | Progress Tracking & KPI Reporting | 2024-06-01 | 2024-11-30 | Project Manager & Analysts
Phase 4 | Risk Management & Issue Resolution | 2024-06-15 | 2024-11-30 | Risk Officer & PMO
Closure & Handover
Phase 5 | User Training & Documentation | 2024-10-01 | 2024-11-30 | Training Team & IT Support
Phase 5 | Closure Report & Lessons Learned Workshop | 2024-11-15 | 2024-12-05 | Project Manager & Stakeholders
Phase 5 | Final Sign-off & Project Handover | 2024-11-30 | 2024-12-15 | Executive Sponsor & PMO
This project plan template is designed for large-scale business environments with structured data collection and reporting. Last updated on April 1, 2024.