## Project Plan - Manager View
Project Plan - Manager View
Task ID | Task Name | Owner | Start Date | End Date | Status | % Complete
P-001 | Project Initiation & Planning | John Smith | 2024-01-15 | 2024-01-31 | On Track | 85%
P-002 | Requirement Gathering | Sarah Johnson | 2024-02-01 | 2024-02-15 | On Track | 95%
P-003 | Design Phase | Mike Davis | 2024-02-16 | 2024-03-15 | On Track | 75%
P-004 | Development Sprint 1 | Lisa Brown | 2024-03-16 | 2024-04-15 | On Track | 55%
P-005 | Development Sprint 2 | Lisa Brown | 2024-04-16 | 2024-05-15 | On Track | 35%
P-006 | User Testing & QA | Tom Wilson | 2024-05-16 | 2024-06-15 | Delayed | 15%
P-007 | Deployment & Go-Live | Jessica Lee | 2024-06-16 | 2024-07-15 | On Track | 5%
M-01 | Project Kickoff Meeting | John Smith | 2024-01-15 | 2024-01-15 | Milestone Complete | 100%
M-02 | Requirements Sign-off | Sarah Johnson | 2024-02-15 | 2024-02-15 | Milestone Complete | 100%
M-03 | Design Approval | Mike Davis | 2024-03-15 | 2024-03-15 | Milestone Complete | 100%
Project Overview
Project Name:Digital Transformation Initiative
Status:On Track (87% Overall Completion)
Total Duration:180 days (Jan 15, 2024 – Jul 15, 2024)
Next Milestone:User Testing & QA (Scheduled: May 16, 2024)