## Project Plan - Planning View
Project Plan - Planning View
Task ID | Task Description | Owner | Start Date | End Date | Status | % Complete
P-001 | Project Initiation and Planning | John Doe | 2023-10-01 | 2023-10-15 | In Progress | 75%
P-002 | Requirements Gathering | Jane Smith | 2023-10-16 | 2023-11-05 | Not Started | 0%
P-003 | Design Phase | Mike Johnson | 2023-11-06 | 2023-11-30 | Not Started | 0%
P-004 | Development Phase | Sarah Wilson | 2023-12-01 | 2024-01-31 | Not Started | 0%
P-005 | Testing and QA | Lisa Brown | 2024-02-01 | 2024-03-15 | Not Started | 0%
P-006 | Deployment and Go-Live | David Lee | 2024-03-16 | 2024-03-31 | Not Started | 0%
Project Summary
Total Tasks: |  | 6
Completed: |  | 0
In Progress: |  | 1
Not Started: |  | 5
Notes
This project plan outlines key milestones, responsibilities, and timelines for successful project execution. Regular reviews are recommended to track progress and adjust accordingly.