## Project Plan - Data Collection
Project Plan - Data Collection
Task ID | Task Description | Responsible Person | Start Date | End Date | Status | % Complete
TASK001 | Define Data Collection Requirements | Jane Doe | 2024-04-01 | 2024-04-05 | In Progress | 75%
TASK002 | Develop Data Collection Forms | John Smith | 2024-04-06 | 2024-04-15 | In Progress | 50%
TASK003 | Test Forms with Pilot Group | Alice Johnson | 2024-04-16 | 2024-04-25 | To Do | 0%
TASK004 | Deploy Data Collection System | Robert Brown | 2024-04-26 | 2024-05-10 | To Do | 0%
TASK005 | Collect and Validate Data | Lisa White | 2024-05-11 | 2024-06-15 | To Do | 0%
TASK006 | Finalize Reports and Documentation | Mary Taylor | 2024-06-16 | 2024-07-15 | To Do | 0%