## Worksheet
Quarterly Project Plan - Data Collection
Q1: January 2024 - March 2024
Task ID | Task Description | Responsible Team | Start Date | End Date | Status | Milestones/Notes
Project Initialization & Planning Phase
T01 | Define data collection objectives and KPIs | Project Team, Data Analysts | 2024-01-01 | 2024-01-15 | In Progress | Finalize goals and success metrics
T02 | Design data collection instruments (forms, surveys) | Data Design Team | 2024-01-16 | 2024-01-31 | To Do | Review and validate templates
Data Collection Implementation Phase
T03 | Deploy data collection tools across departments | IT & Operations Team | 2024-02-01 | 2024-02-15 | To Do | Ensure system compatibility and access rights
T04 | Conduct initial data collection (pilot phase) | Data Collectors, Field Staff | 2024-02-16 | 2024-03-15 | To Do | Gather feedback and identify issues
Data Review & Reporting Phase
T05 | Validate data quality and clean datasets | Data Analysts, QA Team | 2024-03-16 | 2024-03-31 | To Do | Perform data audits and corrections
Q1 Summary Report (End of Quarter)
Q2: April 2024 - June 2024
Full-Scale Data Collection Phase
T06 | Roll out full data collection across all sites/units | Field Operations, Data Team | 2024-04-01 | 2024-05-31 | To Do | Maintain consistent data entry practices
Q3: July 2024 - September 2024
Data Analysis & Insights Phase
T07 | Perform initial data analysis and trend identification | Data Science Team | 2024-07-01 | 2024-08-31 | To Do | Generate first-quarter reports and dashboards
Q4: October 2024 - December 2024
Final Reporting & Evaluation Phase
T08 | Compile comprehensive quarterly report and recommendations | Project Manager, Data Analysts | 2024-10-01 | 2024-12-31 | To Do | Presentation to stakeholders and leadership review
Project End-of-Year Review (December 31, 2024)