## Project Plan - Report Version
Project Plan - Report Version
Task ID | Task Description | Assigned To | Status | Start Date | End Date | Budget (USD)
PJ001 | Project Initiation & Planning | John Doe | Completed | 2024-01-05 | 2024-01-15 | $5,000.00
PJ002 | Requirements Gathering | Jane Smith | In Progress | 2024-01-16 | 2024-01-31 | $8,500.00
PJ003 | Design Phase | Mike Johnson | Not Started | 2024-02-01 | 2024-02-15 | $15,000.00
PJ004 | Development Implementation | Sarah Wilson | Not Started | 2024-02-16 | 2024-03-31 | $50,000.00
PJ005 | Testing & QA | David Brown | Not Started | 2024-04-01 | 2024-04-30 | $18,750.00
PJ006 | Deployment & Go-Live | Lisa Taylor | Not Started | 2024-05-01 | 2024-05-15 | $7,800.00
PJ007 | Post-Implementation Review | Robert Clark | Not Started | 2024-05-16 | 2024-05-31 | $4,500.00
Total Project Cost: | [5 empty] | $119,550.00