## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority
1 | Project Initiation | John Doe | 2024-01-05 | 2024-01-10 | To Do | High
2 | Requirements Gathering | Jane Smith | 2024-01-11 | 2024-01-25 | In Progress | High
3 | Design Phase | Mike Brown | 2024-01-26 | 2024-02-10 | To Do | Moderate
4 | Development Start | Lisa Wong | 2024-02-11 | 2024-03-15 | To Do | High
5 | Testing Phase | Tom Anderson | 2024-03-16 | 2024-04-10 | To Do | Moderate
6 | Deployment & Handover | Sarah Lee | 2024-04-11 | 2024-04-30 | To Do | High