## Worksheet
Project Plan - Small Business
Task ID | Task Description | Responsible Person | Start Date | End Date | Status
101 | Project Initiation | Jane Doe | 2025-04-01 | 2025-04-05 | In Progress
102 | Market Research | John Smith | 2025-04-06 | 2025-04-15 | To Do
103 | Requirement Analysis | Alice Brown | 2025-04-16 | 2025-04-25 | To Do
104 | Design Phase | Mike Wilson | 2025-04-26 | 2025-05-10 | To Do
105 | Development Phase | Taylor Lee | 2025-05-11 | 2025-06-15 | To Do
106 | Testing & QA | Sarah Davis | 2025-06-16 | 2025-07-15 | To Do
107 | Deployment & Training | Chris Evans | 2025-07-16 | 2025-07-31 | To Do
108 | Project Review & Closure | Jane Doe | 2025-08-01 | 2025-08-10 | To Do
Total Tasks: |  |  |  |  | 8