## Worksheet
Startup Project Plan - Data Collection
Task ID | Task Description | Assigned To | Status | Start Date | End Date | Budget (USD)
TASK001 | Define data collection objectives | Alice Johnson | In Progress | 2024-06-15 | 2024-06-25 | $1,500.00
TASK002 | Design data collection forms & surveys | Bob Smith | To Do | 2024-06-18 | 2024-06-30 | $3,750.00
TASK003 | Set up data collection tools (APIs & databases) | Carol Lee | In Progress | 2024-06-16 | 2024-07-15
TASK004 | Recruit and train data collection team | Daniel Kim | To Do | 2024-06-31
Project Milestone: Data Collection Phase Complete - July 31, 2024
TASK005 | Initial data gathering (Pilot Group) | Eva Brown | Not Started | 2024-07-16
TASK006 | Data validation and cleaning process setup
Budget Summary: $35,000.00 / $35,000.09 (Completed)