## Project Plan Summary View
Project Phase | Task Name | Start Date | End Date | Status | Responsible Team | Budget (USD)
Initiation | Define Project Scope | 2024-01-05 | 2024-01-15 | In Progress | Project Management Office | $15,000
Planning | Create Work Breakdown Structure | 2024-01-16 | 2024-01-31 | Not Started | Project Planning Team | $8,500
Execution | Resource Allocation and Mobilization | 2024-02-01 | 2024-03-15 | Not Started | Operations Team | $75,000
Execution | Development and Testing Phase 1 | 2024-03-16 | 2024-05-31 | Not Started | R&D Team | $180,000
Total Project Budget: | [5 empty] | $278,500