## Project Plan Template
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Description
T001 | Project Initiation | John Doe | 2024-04-01 | 2024-04-15 | In Progress | Define project scope and objectives.
T002 | Requirements Gathering | Jane Smith | 2024-04-16 | 2024-05-15 | To Do | Collect detailed requirements from stakeholders.
T003 | Design Phase | Mike Johnson | 2024-05-16 | 2024-06-30 | To Do | Create system architecture and UI/UX designs.
T004 | Development | Emily Brown | 2024-07-01 | 2024-10-31 | To Do | Implement the system based on design specifications.
T005 | Testing Phase | David Lee | 2024-11-01 | 2024-11-30 | To Do | Conduct unit, integration, and user acceptance testing.
T006 | Deployment | Sarah Wilson | 2024-12-01 | 2024-12-15 | To Do | Deploy the system to production environment.
T007 | Post-Implementation Review | John Doe | 2024-12-16 | 2024-12-31 | To Do | Evaluate project success and document lessons learned.
Purpose:Data Collection
Template Type:Project Plan
Style/Version:Template Version