## Worksheet
Project Planning View - Data Collection Template
Task ID | Task Description | Responsible Team Member | Start Date | End Date | Status
P-001 | Define project objectives and scope | Project Manager | 2023-10-01 | 2023-10-05 | In Progress
P-002 | Identify data sources and collection methods | Data Analyst | 2023-10-06 | 2023-10-15 | Not Started
P-003 | Design data collection forms and templates | UX Designer, Data Analyst | 2023-10-16 | 2023-10-25 | Not Started
P-004 | Validate forms with pilot group (if applicable) | Data Analyst, QA Lead | 2023-10-26 | 2023-11-05 | Not Started
Data Collection Phase
P-005 | Begin data collection across all sources | Data Collectors (Team A) | 2023-11-06 | 2023-12-15 | Not Started
P-006 | Monitor data quality and accuracy in real-time | Data Quality Team | 2023-11-06 | 2023-12-15 | Not Started
Data Management & Reporting
P-007 | Organize and clean collected data sets | Data Analyst, IT Support | 2023-12-16 | 2024-01-15 | Not Started
Project Closeout
P-008 | Finalize documentation and deliverables | Project Manager, Documentation Lead | 2024-01-16 | 2024-01-31 | Not Started
Key Metrics & Progress Summary
Total Tasks: | 8 |  | Completed: | 0 (0%)
On Track: | 6 (75%) |  | Delayed: | 0 (0%)
Next Review Date: | 2023-11-30