## Worksheet
Project Timeline - Advanced Template
Task ID | Task Name | Description | Start Date | End Date | Assigned To | Status
T001 | Project Initiation | Define project scope, objectives, and stakeholders. | 2025-04-01 | 2025-04-15 | Jane Doe | Completed
T002 | Requirements Gathering | Capture detailed functional and non-functional requirements. | 2025-04-16 | 2025-04-30 | John Smith | In Progress
T003 | Design Phase | Create system architecture and UI/UX wireframes. | 2025-05-01 | 2025-05-15 | Alice Johnson | In Progress
T004 | Development Sprint 1 | Build core modules and backend services. | 2025-05-16 | 2025-06-15 | Mark Wilson, Sarah Lee | In Progress
T005 | Testing & QA | Execute test cases and resolve bugs. | 2025-06-16 | 2025-07-15 | Lisa Brown | Delayed
T006 | User Training | Prepare training materials and conduct sessions. | 2025-07-16 | 2025-07-31 | Peter Clark | Completed
T007 | Deployment & Go Live | Launch the system in production environment. | 2025-08-01 | 2025-08-15 | Robert Taylor | Completed
T008 | Post-Launch Review | Evaluate project outcomes and document lessons learned. | 2025-08-16 | 2025-08-31 | Jane Doe, John Smith | Completed
Total Tasks:8 ¦Completed:5 ¦In Progress:2 ¦Delayed:1