## Worksheet
PROJECT TIMELINE - ANALYSIS VIEW
Phase | Task Name | Start Date | End Date | Status | % Complete | Owner | Risk Level | Budget Allocated ($) | Notes / Comments
Initiation | Project Charter Approval | 2024-01-05 | 2024-01-15 | Delayed | 65% | Jane Smith | High | 5,000 | Waiting on executive sign-off.
Planning | Scope Definition & Requirements Gathering | 2024-01-16 | 2024-02-15 | In Progress | 85% | Mark Johnson | Medium | 15,000 | Final client meeting scheduled for 2/10.
Scheduling | Milestone Planning & Timeline Development | 2024-02-16 | 2024-03-15 | Not Started | 0% | Sarah Lee | Low | 8,000 | Dependent on scope finalization.
Execution | Design Phase Implementation | 2024-03-16 | 2024-05-15 | Not Started | 0% | Tom Williams | Low | 35,000 | Waiting on design team availability.
Monitoring & Controlling | Risk Assessment & Mitigation Strategy | 2024-04-15 | 2024-05-31 | In Progress | 70% | Alice Brown | Medium | 6,500 | Quarterly review scheduled.
Total Project Budget: | [8 empty] | 79,500