## Project Timeline - Business Use
Project Timeline - Data Collection
Task ID | Task Description | Start Date | End Date | Status | Responsible Team | Budget (USD)
T001 | Project Initiation & Planning | 2024-04-01 | 2024-04-15 | In Progress | Project Management Office (PMO) | $5,000
T002 | Data Requirements Gathering | 2024-04-16 | 2024-04-30 | Pending | Business Analysts | $3,500
T003 | Data Source Identification & Access Setup | 2024-05-01 | 2024-05-15 | Pending | IT Infrastructure Team | $6,800
T004 | Data Collection & Validation Phase 1 | 2024-05-16 | 2024-06-15 | Pending | Data Collection Team | $8,900
T005 | Data Quality Assessment & Cleaning | 2024-06-16 | 2024-07-15 | Pending | Data Science Team | $7,500
T006 | Phase 1 Reporting & Stakeholder Review | 2024-07-16 | 2024-07-31 | Pending | Analytics & Leadership Team | $4,300
T007 | Data Collection & Validation Phase 2 (Follow-up) | 2024-08-01 | 2024-08-31 | Pending | Data Collection Team | $6,100
T008 | Final Data Integration & System Testing | 2024-09-01 | 2024-09-15 | Pending | IT & QA Team | $5,700
T009 | Project Finalization & Handover Documentation | 2024-09-16 | 2024-10-31 | Pending | PMO & Knowledge Management | $3,900
© 2024 Business Use Project Timeline Template. For internal data collection purposes only.