## Project Timeline - Client View
Project Timeline - Client View
Task | Start Date | End Date | Status | Responsible Team
Project Kickoff Meeting | 2023-10-05 | 2023-10-05 | Completed | Project Management
Requirements Gathering | 2023-10-06 | 2023-10-19 | Completed | Business Analysts
Design Phase (UI/UX) | 2023-10-20 | 2023-11-09 | In Progress | Design Team
Frontend Development | 2023-11-10 | 2024-01-15 | In Progress | Frontend Developers
Backend Development | 2023-11-10 | 2024-01-31 | In Progress | Backend Developers
Integration Testing | 2024-02-01 | 2024-02-15 | Delayed | QA Team
User Acceptance Testing (UAT) | 2024-02-16 | 2024-03-15 | Delayed | Client & QA Team
Deployment Preparation | 2024-03-16 | 2024-03-31 | Delayed | DevOps Team
Final Deployment | 2024-04-01 | 2024-04-15 | Delayed | DevOps & Project Management