## Project Timeline - Data Version
PROJECT TIMELINE - DATA VERSION
Phase | Task Description | Start Date | End Date | Status | Responsible Person
Planning & Preparation
Phase 1 | Define project scope and objectives | 2024-01-05 | 2024-01-15 | In Progress | Jane Smith
Phase 1 | Identify key stakeholders and team members | 2024-01-16 | 2024-01-25 | Pending | John Doe
Data Collection & Processing
Phase 2 | Collect primary data through surveys and interviews | 2024-01-30 | 2024-03-15 | Pending | Alice Johnson
Phase 2 | Compile and validate data sources | 2024-03-16 | 2024-03-31 | Pending | Robert Brown
Analysis & Reporting
Phase 3 | Perform statistical and qualitative analysis | 2024-04-01 | 2024-05-15 | Pending | Susan Lee
Phase 3 | Create visualizations and preliminary reports | 2024-05-16 | 2024-06-15 | Pending | David Kim
Finalization & Delivery
Phase 4 | Review and finalize project deliverables | 2024-06-16 | 2024-07-15 | Pending | Jane Smith
Phase 4 | Present findings to stakeholders and obtain sign-off | 2024-07-16 | 2024-07-31 | Pending | John Doe
Total Duration: |  |  |  |  | 2024-01-05 to 2024-07-31