## Worksheet
Project Phase | Task Name | Timeline |  |  | Responsible Team/Person | Status
|  | Start Date | End Date | Duration (Days)
Initiation | Project Charter Development | 2023-10-01 | 2023-10-15 | 15 | Jane Smith (PM) | In Progress
Initiation | Stakeholder Identification | 2023-10-05 | 2023-10-10 | 6 | John Doe (Admin) | Closed
Planning | Scope Definition | 2023-10-16 | 2023-10-31 | 16 | Jane Smith (PM) | Pending
Planning | Resource Allocation Plan | 2023-10-18 | 2023-11-05 | 19 | Lisa Chen (HR) | In Progress
Execution | Design Phase (UI/UX) | 2023-11-06 | 2023-11-30 | 25 | Alex Johnson (Design) | Pending
Execution | Front-End Development | 2023-11-15 | 2024-01-15 | 60 | Mike Brown (Dev) | Pending
Execution | Back-End Development | 2023-11-20 | 2024-01-31 | 73 | Sarah Wilson (Dev) | Pending
Testing | System Integration Testing | 2024-01-16 | 2024-01-31 | 16 | Tom Reed (QA) | Pending
Testing | User Acceptance Testing (UAT) | 2024-02-01 | 2024-02-15 | 15 | Jane Smith (PM) | Pending
Closure | Final Review & Sign-Off | 2024-02-16 | 2024-02-19 | 4 | Jane Smith (PM) | Pending
Closure | Project Documentation & Handover | 2024-02-19 | 2024-03-15 | 35 | All Teams (PM) | Pending
Total Duration |  | 168 days