## Worksheet
Project Timeline - Extended Template
Data Collection ¦ Purpose: Project Planning & Monitoring
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Responsible Team/Person | % Complete
Phase 1: Project Initiation
PRJ001 | Project Kickoff Meeting | 2024-03-01 | 2024-03-05 | 5 | In Progress | Project Manager, Team Leads
PRJ002 | Define Project Scope | 2024-03-06 | 2024-03-15 | 10 | In Progress | Business Analyst, PMO
Phase 2: Planning & Design
PRJ003 | Develop Detailed Project Plan | 2024-03-16 | 2024-03-31 | 16 | In Progress | Project Manager, Planning Team
PRJ004 | Design System Architecture | 2024-04-01 | 2024-04-15 | 15 | Pending | Lead Architect, Dev Team
Phase 3: Development
PRJ005 | Frontend Development (UI) | 2024-04-16 | 2024-05-31 | 46 | Pending | Frontend Developers, UX Designers
PRJ006 | Backend Development (APIs) | 2024-04-16 | 2024-05-31 | 46 | Pending | Backend Developers, DevOps
Phase 4: Testing
PRJ007 | Unit & Integration Testing | 2024-06-01 | 2024-06-30 | 30 | Pending | QA Engineers, Dev Team
Phase 5: Deployment
PRJ008 | Production Deployment (v1.0) | 2024-07-01 | 2024-07-15 | 15 | Pending | DevOps, Deployment Team
Phase 6: Post-Deployment & Review
PRJ009 | User Training & Onboarding | 2024-07-16 | 2024-07-31 | 16 | Pending | Training Team, Support Staff
PRJ010 | Project Retrospective & Closure | 2024-08-01 | 2024-08-15 | 15 | Pending | Project Manager, Stakeholders
Total Duration: |  |  |  | 213 days