## Worksheet
Project Timeline - Data Collection
Task ID | Task Description | Start Date | End Date | Status | Responsible Person
TASK001 | Define project scope and objectives | 2023-10-01 | 2023-10-05 | In Progress | Alice Johnson
TASK002 | Develop data collection instruments (surveys, forms) | 2023-10-06 | 2023-10-15 | Pending | Bob Smith
TASK003 | Recruit participants and obtain consent | 2023-10-16 | 2023-10-25 | Pending | Carol Davis
TASK004 | Campaign and distribute data collection tools | 2023-10-26 | 2023-11-15 | Pending | Daniel Lee
TASK005 | Collect and validate data entries | 2023-11-16 | 2023-12-05 | Pending | Eva Martinez
TASK006 | Finalize data set and prepare for analysis | 2023-12-06 | 2023-12-15 | Pending | Frank Brown
TASK007 | Archive collected data and documentation | 2023-12-16 | 2023-12-31 | Pending | Gina White