## Worksheet
Project Timeline - Large Business Style
Data Collection ¦ Q3 2024 - Q2 2025
Project Phase | Task Name | Start Date | End Date | Status | Owner | Budget (USD)
Planning & Initiation | Define Project Scope | 2024-07-01 | 2024-07-15 | Completed | Jane Smith (PM) | $8,500
Planning & Initiation | Stakeholder Identification | 2024-07-16 | 2024-07-31 | Completed | Jane Smith (PM) | $3,200
Design & Development | System Architecture Design | 2024-08-01 | 2024-10-31 | Ongoing | Robert Lee (CTO) | $45,600
Design & Development | UI/UX Prototyping | 2024-09-15 | 2024-11-30 | Ongoing | Lisa Chen (Lead Designer) | $38,750
Implementation | Backend Development | 2024-11-01 | 2025-01-31 | Delayed | Daniel Kim (Lead Dev) | $78,900
Implementation | Frontend Development | 2024-12-15 | 2025-03-31 | Ongoing | Maria Gonzalez (Frontend Lead) | $69,400
Testing & QA | Unit & Integration Testing | 2025-02-15 | 2025-03-31 | Delayed | Sarah Patel (QA Lead) | $47,800
Testing & QA | User Acceptance Testing (UAT) | 2025-04-15 | 2025-05-31 | Completed | Alex Turner (Product Owner) | $36,900
Total Budget | [5 empty] | $407,050