## Project Timeline - Manager View
Project Timeline - Manager View
Task ID | Task Name | Description | Start Date | End Date | Status | Assigned To
T001 | Project Initiation | Define scope, objectives, and stakeholders. | 2024-01-15 | 2024-01-31 | Completed | Jane Smith
T002 | Requirements Gathering | Capture functional and non-functional requirements. | 2024-02-01 | 2024-02-15 | In Progress | Mike Johnson
T003 | Design Phase | Create system architecture and UI mockups. | 2024-02-16 | 2024-03-15 | In Progress | Sarah Lee
T004 | Development Phase 1 | Frontend development with React components. | 2024-03-16 | 2024-04-30 | Delayed | David Brown
T005 | Backend Development | API development and database setup. | 2024-04-01 | 2024-05-31 | In Progress | Amanda White
T006 | Testing & QA | Unit, integration, and system testing. | 2024-06-01 | 2024-07-15 | Completed | Lisa Green
T007 | User Training | Prepare training materials and conduct sessions. | 2024-07-16 | 2024-08-15 | Completed | Kevin Patel
T008 | Go-Live & Deployment | Launch project in production environment. | 2024-08-16 | 2024-09-30 | Completed | Eva Martin