## Project Timeline - Multi Page
Project Timeline - Phase 1
Task ID | Task Name | Description | Start Date | End Date | Status
T001 | Project Initiation | Define project scope, objectives, and stakeholders. | 2024-01-05 | 2024-01-15 | In Progress
T002 | Requirements Gathering | Capture detailed functional and non-functional requirements. | 2024-01-16 | 2024-01-31 | Pending
T003 | Design Phase I (UI/UX) | Develop wireframes and user interface mockups. | 2024-02-01 | 2024-02-15 | Pending
T004 | Technical Design & Architecture | Define system architecture, database schema, and API specs. | 2024-02-16 | 2024-03-15 | Pending
T005 | Risk Assessment & Planning | Identify project risks and develop mitigation strategies. | 2024-01-18 | 2024-01-31 | In Progress
Data Collection Template ¦ Project Timeline (Multi Page) ¦ Generated: 2024-01-05
Project Timeline - Phase 2
Task ID | Task Name | Description | Start Date | End Date | Status
T006 | Development (Frontend) | Implement user interface components based on design. | 2024-03-18 | 2024-05-15 | Pending
T007 | Development (Backend) | Build server-side logic, APIs, and database integration. | 2024-03-18 | 2024-05-31 | Pending
T008 | Database Setup & Migration | Create and populate initial database with test data. | 2024-03-15 | 2024-03-31 | Pending
T009 | Integration Testing (SIT) | Test integration between frontend and backend components. | 2024-06-01 | 2024-06-30 | Pending
T010 | Code Review & Refactoring | Peer review of code and optimize for performance. | 2024-05-16 | 2024-06-15 | Pending
Data Collection Template ¦ Project Timeline (Multi Page) ¦ Generated: 2024-01-05
Project Timeline - Phase 3
Task ID | Task Name | Description | Start Date | End Date | Status
T011 | User Acceptance Testing (UAT) | Test application with real users and gather feedback. | 2024-07-01 | 2024-07-31 | Pending
T012 | Deployment Preparation | Finalize deployment configuration and scripts. | 2024-08-01 | 2024-08-15 | Pending
T013 | Production Deployment | Deploy application to production environment. | 2024-08-16 | 2024-08-31 | Pending
T014 | Post-Launch Monitoring & Support | Monitor system performance and address critical issues. | 2024-09-01 | 2024-10-31 | Pending
T015 | Project Closure & Documentation Finalization | Archive project data and prepare final report. | 2024-11-01 | 2024-11-30 | Pending