## Project Timeline - Office Use
Project Timeline - Data Collection Template
Task ID | Task Description | Start Date | End Date | Responsible Party
|  |  |  | Team Member | Role | Status
T001 | Project Initiation & Planning | 2024-01-05 | 2024-01-15 | Jane Doe | Project Manager | In Progress
T002 | Requirements Gathering | 2024-01-16 | 2024-01-31 | John Smith | Business Analyst | Pending Review
T003 | Design Phase - Wireframes & Prototypes | 2024-02-01 | 2024-02-15 | Alice Johnson | UX Designer | Not Started
T004 | Development - Frontend Implementation | 2024-02-16 | 2024-03-15 | Robert Brown | Frontend Developer | Not Started
T005 | Development - Backend Implementation | 2024-02-16 | 2024-03-31 | Lisa White | Backend Developer | Not Started
T006 | Testing & QA Phase | 2024-04-01 | 2024-05-15 | Mary Green | QA Engineer | Not Started
T007 | User Acceptance Testing (UAT) | 2024-05-16 | 2024-06-15 | David Lee | Product Owner | Not Started
T008 | Deployment & Go-Live Preparation | 2024-06-16 | 2024-07-15 | Sarah Kim | DevOps Engineer | Not Started
T009 | Post-Launch Review & Documentation Finalization | 2024-07-16 | 2024-07-31 | Jane Doe | Project Manager | Not Started
This project timeline template is designed for Office Use and can be exported to Excel for further data collection and analysis.