## Worksheet
Project Timeline - Planning View
Purpose: Data Collection
Task ID | Task Name | Start Date | End Date | Status | Responsible Team | Milestone?
TASK001 | Project Initiation | 2024-06-15 | 2024-06-25 | In Progress | Project Team A | No
TASK002 | Requirements Gathering | 2024-06-26 | 2024-07-15 | Not Started | Business Analysts | No
MIL001 | Requirements Finalized | 2024-07-15 | 2024-07-15 | Not Started | Project Team A | Yes
TASK003 | System Design Phase | 2024-07-16 | 2024-08-15 | Not Started | Development Team B | No
MIL002 | Design Approval Complete | 2024-08-15 | 2024-08-15 | Not Started | Project Manager | Yes
TASK004 | Development & Coding | 2024-08-16 | 2024-10-31 | Not Started | Dev Team C/D/E | No
MIL003 | Development Complete - UAT Ready | 2024-10-31 | 2024-10-31 | Not Started | Lead Developer | Yes
TASK005 | User Acceptance Testing (UAT) | 2024-11-01 | 2024-11-30 | Not Started | QA Team & Stakeholders | No
MIL004 | UAT Sign-Off Achieved | 2024-11-30 | 2024-11-30 | Not Started | CPO & Project Sponsor | Yes
TASK006 | Deployment to Production | 2024-12-01 | 2024-12-15 | Not Started | DevOps Team | No
MIL005 | Project Go-Live Complete | 2024-12-15 | 2024-12-15 | Not Started | All Teams | Yes
Data Collection Template ¦ Planning View ¦ Project Timeline