## Worksheet
Task ID | Task Description | Start Date | End Date | Status | Responsible Person
PT001 | Project Initiation & Planning | 2024-03-01 | 2024-03-15 | In Progress | Jane Doe
PT002 | Data Requirements Gathering | 2024-03-16 | 2024-03-31 | Pending | John Smith
PT003 | Data Source Identification | 2024-04-01 | 2024-04-15 | Pending | Alice Johnson
PT004 | Data Collection Phase 1 | 2024-04-16 | 2024-05-15 | Pending | Robert Brown
PT005 | Data Validation & Cleaning | 2024-05-16 | 2024-06-15 | Pending | Sarah Lee
PT006 | Data Integration & Storage Setup | 2024-06-16 | 2024-07-15 | Pending | Mike Wilson
PT007 | Data Analysis & Reporting Preparation | 2024-07-16 | 2024-08-15 | Pending | Lisa Garcia
PT008 | Final Review & Approval | 2024-08-16 | 2024-09-15 | Pending | Jane Doe
PT009 | Project Closure & Documentation Finalization | 2024-09-16 | 2024-10-31 | Pending | All Team Members
Note: This printable timeline is intended for internal project management use. Update statuses regularly.