## Worksheet
Project Timeline - Small Business
Task | Start Date | End Date | Status | Responsible Party
Project Initiation & Planning | 2023-10-01 | 2023-10-15 | Complete | Jane Doe
Market Research & Analysis | 2023-10-16 | 2023-10-31 | In Progress | Mike Smith
Product Design & Prototyping | 2023-11-01 | 2023-11-30 | In Progress | Sarah Johnson
Marketing Strategy Development | 2023-11-01 | 2023-11-20 | In Progress | Lisa Brown
Prototype Testing & Feedback | 2023-12-01 | 2023-12-15 | Delayed | Derek Lee
Final Product Refinement | 2023-12-16 | 2024-01-15 | In Progress | Sarah Johnson
Marketing Campaign Launch | 2024-01-16 | 2024-01-31 | Delayed | Lisa Brown
Product Launch Event | 2024-02-01 | 2024-02-15 | In Progress | Jane Doe
Post-Launch Review & Reporting | 2024-02-16 | 2024-03-15 | In Progress | Mike Smith