## Project Timeline Summary View
Project Phase | Start Date | End Date | Status | Responsible Team | Milestones Achieved (%)
Project Initiation | 2023-10-01 | 2023-10-15 | In Progress | Project Management Office | 75%
Requirements Gathering | 2023-10-16 | 2023-11-05 | Pending | Product Team | 0%
Design Phase | 2023-11-06 | 2023-11-30 | Pending | UX/UI Design Team | 0%
Development Phase | 2023-12-01 | 2024-01-31 | Pending | Engineering Team | 0%
Testing & QA | 2024-02-01 | 2024-03-15 | Pending | QA Team | 0%
Deployment & Go-Live | 2024-03-16 | 2024-03-31 | Pending | DevOps Team | 0%
Total Duration | 2023-10-01 to 2024-03-31 |  | Overall Progress | 7%