## Worksheet
Project Timeline - Tracking View
Data Collection Template ¦ Purpose: Project Timeline Tracking
Task ID | Task Description | Start Date | End Date | Status | % Complete | Responsible Person
T001 | Project Initiation & Planning | 2024-04-01 | 2024-04-15 | Completed | 100% | Alice Johnson
T002 | Requirements Gathering | 2024-04-16 | 2024-05-15 | Completed | 100% | Bob Smith
T003 | Design Phase (UI/UX) | 2024-05-16 | 2024-06-30 | In Progress | 75% | Carol Davis
T004 | Frontend Development | 2024-07-01 | 2024-08-31 | In Progress | 55% | Daniel Brown
T005 | Backend Development | 2024-07-15 | 2024-09-15 | In Progress | 60% | Elena Martinez
T006 | Integration Testing | 2024-09-16 | 2024-10-15 | Delayed | 30% | Frank Wilson
T007 | User Acceptance Testing (UAT) | 2024-10-16 | 2024-11-30 | Delayed | 5% | Gina Taylor
T008 | Deployment & Go-Live | 2024-12-01 | 2024-12-31 | Delayed | 0% | Hector Clark
Generated on: