## Project Tracker - Manager View
Project Tracker - Manager View
Project ID | Project Name | Client | Start Date | End Date | Status | % Complete | Budget (USD) | Actual Spend (USD) | Project Manager
PJ001 | Website Redesign Initiative | GlobalTech Inc. | 2024-03-15 | 2024-06-30 | In Progress | 68% | $45,000 | $31,250 | James Wilson
PJ002 | Mobile App Development | Skyline Solutions Ltd. | 2024-01-10 | 2024-11-30 | In Progress | 85% | $78,500 | $66,730 | Sarah Chen
PJ003 | CRM System Integration | FinSecure Financials | 2024-04-01 | 2024-12-15 | In Progress | 37% | $65,000 | $24,180 | Robert Kim
PJ004 | Internal Training Platform | In-House Project | 2023-11-20 | 2024-05-31 | Completed | 100% | $38,900 | $37,456 | Lisa Park
PJ005 | Cloud Migration Project | GlobalData Systems | 2024-03-01 | 2024-11-30 | Delayed | 55% | $98,650 | $43,790 | David Patel
PJ006 | E-Commerce Platform Upgrade | ShopWell Retail Co. | 2024-05-15 | 2024-10-31 | On Hold | 9% | $57,800 | $5,432 | Emily Rivera
Note:This template is designed for project tracking with key performance indicators. Use the status indicators to quickly identify project health at a glance.