## Project Tracker - Multi Page
Project ID | Project Name | Start Date | End Date | Status | Budget (USD)
PJ001 | Website Redesign | 2023-01-15 | 2023-04-30 | In Progress | $45,000.00
PJ002 | Mobile App Development | 2023-03-10 | 2023-11-15 | Planning | $89,500.00
PJ003 | CRM Integration | 2023-05-22 | 2024-12-31 | On Hold | $67,800.00
Team Assignments & Milestones (Page 1)
PJ001 | UX/UI Design Phase | 2023-01-15 | 2023-02-15 | In Progress | -
PJ001 | Frontend Development Phase | 2023-02-16 | 2023-04-15 | Pending Start | -
Budget Allocation & Expenses (Page 1)
PJ001 | Design Team | - | - | $12,000.00 | $12,567.34
PJ001 | Development Team | - | - | $28,500.00 | $25,341.98
Project ID | KPI Category | Target Value | Actual Value | Status (Progress)
PJ001 | Timeline Adherence | 100% | 95% | In Progress
PJ001 | Bug Resolution Rate (per week) | 95% | 87% | Slight Delay
Resource Utilization (Page 2)
PJ001 | Project Manager Hours (Total) | -83/9092%
PJ001 | Dev Team Utilization Rate
Risk Assessment (Page 2)
PJ001 | Risk Factor | Probability (High/Med/Low) | Impact (High/Med/Low) th>Overall Risk Level
Page 2 - Summary & Notes
The Website Redesign project is on track with minor delays in backend integration. Additional QA resources recommended for next sprint.
Project ID | Dependency ID | Description of Dependency | Predecessor Task(s) | Status (Open/Completed)
PJ001 | DEP001 | API Integration with Payment Gateway | PJ001 - Phase 2 Final Testing (Due: 2023-4-3) | In Progress
PJ001 | DEP002 | Approval from Client Legal Team on Design Assets
Gantt Chart Overview (Text Representation)
[Project ID: PJ001] ¦ [Jan 15 – Feb 8]: UI Design ¦ [Feb 9 – Apr 1]: Development ¦ [Apr 2 – Apr 30]: Testing & QA