## Worksheet
Schedule Planner - Analysis View
Date | Activity Type |  |  |  | Resource Allocation |  |  | Status
| Task Name | Category | Priority | Duration (hrs) | Team Member(s) | Type | # of Units(or Hours)
Weekly Planning - Q3 2024 (Week 1)
2024-07-08 | Project Kickoff Meeting | Planning | High | 2.5 | Alice Chen, Bob Wilson | Personnel(Full-Time)2.5 hrs each (Total: 5)In Progress
2024-07-09 | Data Gathering Phase | Research | High | 4.0Chris Rivera, Diana Liu, Emma ZhangPersonnel (Part-Time)12 hrs total (4 hrs each)Status: Pending
2024-07-10 | System Requirements Review | Analysis | Medium3.5 hrs (team)Team Meeting (Virtual)3.5 hrs total (all present)Status: Not Started
2024-07-11 | Design Wireframe Draft | DevelopmentHigh6.0 hrs (designer)John Smith (Lead Designer)Personnel (Full-Time)Status: In Progress
2024-07-12 | Stakeholder Feedback Session | CommunicationMedium1.5 hrs (team)All Teams InvolvedVirtual Meeting (3hrs total)Status: Scheduled
Weekly Planning - Q3 2024 (Week 2)
2024-07-15 | Backend API Development | DevelopmentHigh8.0 hrs (Dev Team)Alex Kim, Taylor Reed, Jordan LeePersonnel (Full-Time)Status: Not Started
2024-07-16 | UX Testing Preparation | Testing & QAMedium3.5 hrs (team)Morgan Patel, Quinn Foster, Casey LeePersonnel (Part-Time)Status: In Progress
2024-07-17 | Data Validation Scripting | AnalysisHigh4.5 hrs (data analyst)Riley Turner, Sam Wright (Lead Analyst)Personnel (Full-Time)Status: Pending
2024-07-18 | Mid-Sprint Review Meeting | PlanningMedium2.0 hrs (team)All Leads & ManagersMeeting Time (2 hrs total)Status: Scheduled
2024-07-19 | Documentation Update - Phase 1 | AdministrationLow3.0 hrs (writer)Sasha Bloom, Jordan Lee (co-author)Personnel (Part-Time)Status: Not Started