## Task Manager - Client View
Task Manager - Client View
Task ID | Task Title | Description | Assignee | Status | Due Date | Priority
TASK001 | Project Requirements Finalization | Finalize all project requirements with client approval. | Jane Smith | Pending | 2024-01-15 | High
TASK002 | UI/UX Design Review | Conduct design review session with stakeholders. | Mike Johnson | In Progress | 2024-01-20 | Medium
TASK003 | Backend API Development | Complete development of core backend APIs. | Sarah Williams | In Progress | 2024-01-18 | High
TASK004 | User Testing Preparation | Prepare test scenarios and user guides. | David Brown | Pending | 2024-01-25 | Low
TASK005 | Final Deployment & Sign-off | Deploy final version and obtain client sign-off. | Linda Taylor | Completed | 2024-01-10 | High